## Wave Metrics
Wave metrics and expansion gate
SAMPLE DATA - illustrative only. Replace blue cells with your own telemetry and survey results.
Wave | Population | Licensed devs | Active (28d) | Suggestions shown | Suggestions accepted | Satisfaction (1-5) | Trust (1-5) | Change failure rate | Revert rate | Activation | Acceptance rate | Gates passed (of 5) | Decision
Wave 0 | Platform + security pilot | 25 | 23 | 18200 | 5600 | 4.4 | 3.9 | 11.5% | 3.8% | 92% | 30.77% | 5 | EXPAND
Wave 1 | Pilot teams + champions | 80 | 58 | 52000 | 14700 | 4.2 | 3.7 | 12.1% | 4.1% | 72.5% | 28.27% | 5 | EXPAND
Wave 2 | ~40% of engineering | 160 | 104 | 96000 | 24000 | 3.9 | 3.5 | 12.8% | 4.3% | 65% | 25% | 4 | HOLD - FIX GAPS
Wave 3 | Remaining engineering | 135 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0 | NOT STARTED
Total |  | 400 | 185 | 166200 | 44300 |  |  |  |  | 46.25% | 26.65%

## Champions
Champion network
SAMPLE DATA. Coverage check flags waves with too few champions.
Champion | Team | Wave | Hours / week | Sessions held | Issues raised | Cohort NPS
Champion A | Payments | 1 | 4 | 6 | 9 | 42
Champion B | Platform | 1 | 4 | 8 | 14 | 55
Champion C | Mobile | 1 | 3 | 5 | 6 | 31
Champion G | Security | 1 | 2 | 3 | 4 | 38
Champion D | Data | 2 | 4 | 4 | 7 | 28
Champion E | Web | 2 | 3 | 5 | 5 | 36
Champion F | Identity | 2 | 4 | 3 | 8 | 22
Wave | Developers | Champions | Devs per champion | Coverage
1 | 80 | 4 | 20 | OK
2 | 160 | 3 | 53.3333 | ADD CHAMPIONS

## Impact
Impact model: difference-in-differences and value range
SAMPLE DATA. Treated = AI users, control = matched teams that waited. Use a delivery metric where LOWER is better (e.g., PR cycle time, hours).
Metric (lower is better) | Treated pre | Treated post | Control pre | Control post | Treated change | Control change | Effect (DiD) | Effect %
PR cycle time (hours) | 30 | 21 | 29 | 27.5 | -9 | -1.5 | -7.5 | -25%
Value model (haircut self-reports; report as a range)
Input | Low | Base | High
Developers on tool | 300 | 300 | 300
Hours saved per dev per week (survey-calibrated) | 1 | 2 | 3
Haircut on self-reported hours | 50% | 35% | 20%
Working weeks per year | 46 | 46 | 46
Loaded cost per hour ($) | 95 | 95 | 95
Annual tool + infra cost ($) | 180000 | 180000 | 180000
Net annual value ($) | 475500 | 1524300 | 2966400
ROI (value / cost) | 2.6417 | 8.4683 | 16.48
Note: productivity gains in one metric can coexist with stability losses elsewhere. Keep the change-failure and revert guardrails on the Wave Metrics sheet.

## Settings
Gate thresholds (defaults - calibrate after Wave 0)
Blue = input you can change. A wave expands only if every gate passes.
Gate | Value | Meaning
Min activation (28-day active / licensed) | 60% | Share of licensed developers who used the tool in the last 28 days
Min satisfaction (1-5 survey) | 4 | Average developer satisfaction
Min trust (1-5 survey) | 3.5 | Trust in AI output
Max change-failure-rate increase vs baseline | 10% | Relative increase allowed vs pre-rollout baseline
Max revert-rate increase vs baseline | 10% | Relative increase allowed vs pre-rollout baseline
Baseline change failure rate | 12% | Measured before rollout (DORA)
Baseline revert rate | 4% | Measured before rollout
Max developers per champion | 25 | Champion coverage guardrail (default 15-25)